## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Gestion de projet
| Planification | 2020-06-15 | 15 | 2020-06-16 | 2 | 2 | 0 | All | 100%
| Budget | 2020-06-16 | 16 | 2020-06-19 | 4 | 2 | 2 | Andrea, Majka | 50%
| Rôles | 2020-06-15 | 15 | 2020-06-15 | 1 | 0.8 | 0.2 | All | 80%
| Rapport | 2020-06-16 |  | 2020-06-19 |  |  |  | Filipe | 40%
20%
Modélisation
| Adaptation diagramme de classe | 2020-06-16 | 16 | 2020-06-17 | 2 | 2 | 0 | Léonard | 100%
| Schéma technique | 2020-06-18 | 18 | 2020-06-19 | 2 | 1.6 | 0.4 | Majka | 80%
| Traitements | 2020-06-19 | 19 | 2020-06-23 | 5 | 3 | 2 | Majka | 60%
|  | 2018-01-22 | 22 | 2018-01-26 | 5 | 2 | 3 |  | 40%
Création DB
| Mise en place PgAdmin | 2020-06-24 | 24 | 2020-06-26 | 3 | 3 | 0 | Léonard | 100%
| Remplir table | 2020-06-26 | 26 | 2020-06-29 | 4 | 3.2 | 0.8 | Majka | 80%
| Tests | 2020-06-29 | 29 | 2020-06-30 | 2 | 1.2 | 0.8 | Majka | 60%
UX interface
| Artefact identité visuel | 2020-06-16 | 16 | 2020-06-17 | 2 | 2 | 0 | Filipe, Andrea | 100%
| Bike Test Gryon identité visuel | 2020-06-18 | 18 | 2020-06-19 | 2 | 1.6 | 0.4 | Filipe, Andrea | 80%
| Mockup | 2020-06-22 | 22 | 2020-06-24 | 3 | 1.8 | 1.2 | Andrea | 60%
| Arborescence site | 2020-06-22 | 22 | 2020-06-22 | 1 | 0 | 1 | All | 0%
| Wireframes | 2020-06-24 | 24 | 2020-06-29 | 6 |  |  | Andrea, Majka
| Personnas | 2020-06-30 | 30 | 31.06.2020 |  |  |  | Majka, Andrea
| Storytelling | 2020-06-30 | 30 | 31.06.2020 |  |  |  | Majka
Benchmark
Backednd
| Installation Laravel | 2020-06-15 | 15 | 2020-06-15 |  |  |  | Léonard
| Migration Seed | 2020-06-26 | 26 | 2020-06-29 |  |  |  | Léonard, Filipe
| Gestion des rôles (4 rôles) | 2020-06-30 | 30 | 2020-07-01 |  |  |  | Filipe, Léonard
Frontend
| CSS (charte graphique) | 2020-07-01 | 1 | 2020-07-06 |  |  |  | Andrea
| Algorithme fonctions | 2020-07-01 | 1 | 2020-07-06 |  |  |  | Filipe, Léonard, Majka
| Controler, Routes | 2020-07-01 | 1 | 2020-07-06 |  |  |  | Filipe, Léonard, Majka
| Vues | 2020-07-01 | 1 | 2020-07-07 |  |  |  | Filipe, Léonard, Majka
| Tests | 2020-07-06 | 6 | 2020-07-07
Présentation |  |  | 0
| Présentation ppt | 2020-07-07 | 7 | 2020-07-09 |  |  |  | Léonard, Andrea
| Rapport final | 2020-06-15 | 15 | 2020-07-09 |  |  |  | Majka, Filipe
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])